VIRTUAL MEETING (Google meet)

September the 26th, 2022

Starting: 9:00 am

Ending: 9:45 am

PARTICIPANTS

LAG Razlog:

- Mariya Manushkina – project coordinator

LAG Serre Calabresi:

- Gregorio Muzzi – Director

- Angelo de Luca – Project Coordinator

- Giampiero Pirro- Consultant WP.6

- Enrico Esposito- Consultant WP5.1

Angelo de Luca opens the meeting by welcoming everyone and recalling the points on the agenda to be discussed.

The first point concerns the platform (WP2). Enrico takes the floor and says him that the platform is the same as last meeting he just have to update it with the feedbacks he receives from the others. So, he will do these last modifications, and he said that the platform will be ready in two weeks. So, he will send an email just now and everyone will answer with his/her feedbacks, so that Emilio can close this issue.

Then Angelo briefly introduced the issue of the methodological manual (WP3), but Mariya confirmed that everything is ready and completed for this topic, so the meeting could easily move on.

The third point of the meeting was about the "innovative projects"(WP6). The 3 strands identified in the last meeting were:

- Waste management (Lag Razlog)

- Rural Tourism (Lag Serre Calabresi)

- Wood supply chain (Lag Serre Calabresi).

Angelo said that he is working on the project about waste management, and the first draft is ready, he will send it to Mariya for her feedback. The main idea is to create a system to use some part of waste management to create organic fertilizing. This project Angelo thinks is feasible, cheap and easy to implement. Then, about the two others projects, there is the need to discuss and to find the ideas. About the development of rural tourism, Angelo suggested that the easiest and most effective project could be the establishment of a long-term and consolidated cooperation between the tourist agencies (maybe specialised in rural tourism) located in Razlog and in Serre Calabresi. In this way, a new wave of tourism can move from Bulgaria to Italy and this could boost the rural tourism. The others liked the idea, so Angelo said that we can go on to write the draft. The third project, about the wood supply chain, no further developments have been made, so now Angelo with the team of LAG Serre Calabresi have to work on it to develop a concrete project proposal.

These three projects are the final outcomes of the whole project, and they will be presented in the next meeting in presence, that will be the closure of the project, in Calabria. Mariya said that for them would be the best to come to Italy in January, Gregorio agreed so he will send some feasible dates.

Angelo concludes the meeting by thanking everyone.

Next tasks:

- Angelo will send the draft for the Waste management project to Mariya;

- LAG Serre Calabresi has to decide the dates for the next meeting in presence in January and to communicate them as soon as possible to LAG Razlog;

- Emilio has to send to everyone by today the email with the details for the platform and the others have to give him back some feedbacks;

- The draft about the rural tourism should be developed;

- LAG Serre Calabresi and Angelo have to work of the development of an idea about the project of wood supply chain.